COMMITTEE   MEETING      14/08/03       Greyhound Social Club

Attendees   Peter, Matt, Amanda, Noel and Sue

Noel away - 28th August - 8th September.       Peter away  8th - 15th September.

AV Entries -  Handed Peter   26 + 7 entries.   Noel advises more entries to come at SPD meeting

Slides will be scanned over the weekend  30/ 31st August by Dave Fagan. Will need an entire weekend and helper. All entries will be pre-sorted.  Dave F. to burn discs.  Need 4 folders?? 1 x each category Masters, open, novice & digital.   Video - 30 seconds then 3 place getter's in full.

Skirmish - is still on although numbers light on.

Judges – Confirmed - Martin Kandilas, Tom Byron,  Peter to ring  Mark Welsh,  Amanda to ring Kim Kohen.

Proposed date for judging  20th September, 2003.  Room 4D to be booked at the B'stown Sports Club. SPD to provide lunch.    ** Room 4D has been booked with  TV, video, screen and only a handful of seats. **

M.C. – Suggested Grant Goldman - Peter to confirm.

Guest Speaker – Do we need one??  15-20 mins.  Peter to phone Dave and see what was happening.

Confirmation of Sponsors – Peter to send confirmation letter to Noel to re-vamp, put on letterhead etc. so we can distribute same.

Brochures - to be sent to???  Matt to check with his Dad to see if we can get them delivered to their work.

Kodak/ Fuji - Peter to send a letter to their promotions/ marketing department.

Tickets - Fab to do printing.  Raffle ticket prizes all but sorted out.

Amanda to see Wilderness for a raffle prize.

Door Prize - Sea & Sea Camera - digital  (Peter to check into type accessories etc.)

10 Memberships as prizes - giveaway's from drawing folder numbers.

Food- Ask dive shops when booking tables re food - at end of August we will need to start telephoning dive shops re table bookings etc.  Suggest 150 patrons for food.   Noel to re-do food tickets.

Promotional Items –  Nothing done yet - Amanda to chase Noel,

suggested getting biro’s (1,000) stickers, coasters etc to put in the folders. Will also get a price on caps – info to be discussed at next meeting.

Tim Williams - will do an informal chat re his dive log/ computer info.

Guest Speaker - next meeting  Steve Cross

