# 5.		The co-management process: a summary view

| a point of departure |  | - assessing the need for co-management and the process feasibility - assessing the available human and financial resources - establishing a Start-up Team |
| --- | --- | --- |

| phase I: organising for the partnership |  | - gathering information and tools (such as maps) on the main ecological and social issues at stake - identifying in a preliminary way the NRM unit(s) and institutional actors at stake - launching and maintaining social communication initiatives on co-management in the local context - contacting the institutional actors, facilitating appraisal exercises and continuing with them the ecological, social and stakeholder analyses - helping the institutional actors to organise and identify their own representatives, as necessary - organising the first meeting of institutional actors and proposing a set of rules and procedures for the negotiation phase, including explicit equity considerations |
| --- | --- | --- |
| phase II: negotiating plans and agreements |  | - agreeing on the negotiation rules and procedures - developing a common vision of the desired future for the NRM unit(s) at stake - ritualising the agreed common vision - reviewing the current socio-ecological situation and trends - agreeing upon a strategy towards the common vision - negotiating specific co-management plans and agreements for each component of the strategy (including clarifying what will be done by whom and with what means; mediating conflicts; establishing zoning arrangements and the sharing of NRM functions, rights and responsibilities among stakeholders; agreeing on follow-up protocols). - agreeing upon CM organisations and initiatives to “institutionalise” CM - legitimising and publicising the co-management plans, agreements and organisations |
| phase III: learning by doing |  | - applying and implementing the co-management plans, agreements and organisations - clarifying the entitlements and responsibilities of the institutional actors, as necessary - collecting data and information on results and process, as specified in the follow-up protocols - identifying the main factors impacting upon natural resources and stakeholders; experimenting judiciously with innovations - organising review meetings at regular intervals to evaluate results and lessons learned; modifying the co-management plans, agreements and organisations, as necessary |