|  | Dates | Task | EH-S | DW | PS | Other Costs |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | 4/6-6/6 | Prepare detailed plan | 140 | 140 | 100 |  |
| 2. | 10/6-12/6 | Steering committee Visit Study Area | 1120 | 1120 | 800 | Travel $ 250 |
| 3. | 16/6-27/6 30/6-18/7 | Prepare Discussion Paper Circulate & consult - include workshops at Melbourne, Canberra ? Prepare training program discussion paper report to steering committee | 1120 | 1120 | 800 | Travel $ 250 Miscell $ 250 |
| 4. | w.c. 28/7 | Steering Committee | 560 |  | 400 | Travel $ 250 |
| 5. | 4/8-15/8 | Prepare draft final report , including training manual Prepare Executive Summary Circulate | 2400 | 1740 | 1600 |  |
| 6. | 18/8-5/9 | Obtain feedback on report | 280 |  |  |  |
| 7 | w.c. 1/9 | Steering Committee | 560 | 560 |  | Travel $ 250 |
| 8. | > 12/9 | Submit final report | 1260 | 560 | 400 |  |
| 9. | Oct | Workshop presentation at Jindabyne |  | 1120 | 800 | Air Travel $ 450 |
|  |  | Total Costing $ 20,000 | $ 7440 | $ 6360 | $ 4500 | $ 1700 |