TOWARDS  A  RECREATION  STRATEGY  AND

MONITORING  PROGRAM  IN  AUSTRALIAN

ALPINE  PARKS  AND  RESERVES

Project  Planning  Paper  2  :  for  Steering  Committee  30.7.97.

Introduction

This paper is partly a progress report, and partly a forward look at aspects of the project.

Material is coming to hand almost daily from the think-tank process. We will up-date further if necessary at the meeting.

Study  Area

We have defined the study area along the lines suggested in our previous paper, but with some modifications to capture specific aspects of recreational activity.

A map will be provided at the meeting.

Report Format :

We will proceed with the concept of the last meeting, i.e.  a three-volume report :

Vol. 1	Background Papers : This would be the substantive report and would include both material from our own study together with key extracts from the literature. It would explain approaches to and the processes of impact management in depth.

Vol 2	An example : This would be a report on the pilot study area, and would serve as a basic case example for both continuing field testing and teaching.

Vol 3	Teaching Workbook : This would be the basic teaching program for rangers, concessionaires and others. It would include not only instructional material, but a range of practical exercises.

Stakeholder Workshops

One workshop is to be held at Buchan on the afternoon of 29th. July. So far, we have a

very positive response to invitations.

The dates for Melbourne and Jindabyne will be set in the next couple of days.

Think-tank Review of First Discussion Paper

The list of those who have received our discussion paper is :

| Steering Committee David Phillips Neville Byrne Peter Jacobs Alan Graefe Larry Hamilton Bill Borrie Steve McCool Joe Roggenbuck George Stankey David Lime Rob Carlisle Per Nilsen Ken Balmer Paul Eagles | Kreg Lindberg Terry de Lacey Brian Finlayson David Gillieson Gordon Cessford Shaun Elwood Adrian Davey Bruce Gall Alison Ramsay Tim Gardner Jim Daly Penny Spoedler Pam O’Brien Jim MacBeth | Warwick Papst Roger Good David Hogg Charles Meredith Wayne Schmidt John Watson Mike Pemberton Kevin Kiernan Chris Sharples Russell Mason Pam Jacobs Ron Sutton John Hepper Gordon Friend |
| --- | --- | --- |

Feedback has been slow - we have some 8 responses to date, together with several

messages saying “I’m working on it !’ However, some of the current responses have

indeed been valuable, and include detailed documentation of similar work in both New

Zealand and Canada.

Some of the key issues which we need to discuss here are :

- Area boundaries

We said : In turning to the question of environmental impact monitoring and management, we plan to utilise a process which we already developed and used elsewhere which draws upon aspects of the LAC, VIM, VERP and other previous planning tools in this area.

Before expanding on this, there is the question of its integration with ROS. Both ROS and any of the schemes for environmental management define areal units. ROS defines these in terms of the character of recreational opportunity provided ; environmental management demands definition in terms of common environmental character and vulnerabilities.

It seems to us that this will often result in different kinds of boundaries. This in our pilot area, commencing with ROS, the valley of the Snowy provides a specific kind of recreation opportunity which integrates not only the river with its riparian environmental association, but the valley sides with a montane forest. But from an environmental management perspective, the river and its riparian association demands different environmental considerations than the montane forests.

***	Does it present any practical problems in having one set of guidelines and

boundaries for recreation planning purposes and another set for

environmental management purposes ?  If so, are these sufficiently important

to justify the imposition of a single set of guidelines and boundaries upon the

land ?

One clear response (from several people, but perhaps most explicitly from Gordon Cessford arising out of NZ experience) is :

‘Recreation and environmental boundaries are not the same and should not be treated that way. Difference is OK because it reflects different management purposes and different values.’

On the other hand, there was some concern that

(i) Having multiple area boundaries may be confusing.

Our response is that certainly clarity is important, and that we should adopt an approach which is easy to use in the field.  However, distinguishing the two kinds of area should not create problems.

(ii)  We should strive for co-incidence in that environmental parameters should

determine the land capability for recreational purposes

This may be an ideal view ; in practice, it might lead to inappropriately complex  and confusing recreational areas where communication with the visitor is important.

- Traditional zoning concepts sometimes cloud the issue by leading people to expect a single set of boundaries based upon managerial perspectives rather than upon recreational or environmental ones.

Agreed.

On balance from the feedback to date and our own experience, we are pretty sure that the two sets of boundaries do not constitute a major problem, and that we should assume that approach will be used. But what are the views from members of  the Steering Committee?

- On Selection of Indicators

It is clear that indicators should be both simple to understand and easy (cheap) to monitor. But a further suggestion is that the focus should be on monitoring only those things which can be controlled by park managers. As a simple example, water levels and at least some dimensions of water quality in the rivers are outside the control of the park managers, and so would not be monitored.

- Some Suggested Indicators

- Proliferation or widening of tracks

- Proliferation or expansion of campsites

- Erosion of stream banks

- Weed invasion

- Damage to vegetation

- re-working of sediment or talus slopes

- removal of dead vegetation for firewood

- removal of understory vegetation

- reduction in tussock grass or other soil-binding vegetation

All of the above may well be measured by photo-monitoring and in some cases by transect or quadrat survey..

- Soil compaction - use of cone penetrometer recommended ; are there simpler reliable methods ?

- Water quality - probably useful immediately above and below campsites or other similar areas. Millipore equipment recommended, but we will seek further specialised advice on this.

- 4.	On Visitors

Some of the literature suggests that visitor information only needs to deal with numbers, distribution and behaviour of visitors. However, we asked :

***	What, in your understanding  and experience, are the most useful parameters

to measure about visitors ? Would you want values, attitudes, quality of

experience or not ? If you would collect this data, what questions would you

focus upon ?

Responses so far suggest that important areas include :

- attitudes (to management and the environment)

- quality of experience.

- visitor rating of impacts

But again, we should make sure we focus upon  those issues over which management has at least some influence.

Towards a Training Program

- OBJECTIVES

Much of the current training rhetoric is about ‘competency-based programming’. This leads to the identification of core tasks and the technical skills necessary to their performance, then teaching these skills.

We are concerned that this approach is inadequate to meet the needs of park management (or, indeed many other fields). One of our colleagues actually has printed on his letterhead the words “It is not useful to do efficiently that which should not be done at all”. In other words, making wise judgements about what should be done is a vital element in good management.

So, we would define the objectives of training for improving the relationship between recreation development and environmental management along the following lines :

| Objective | Notes |
| --- | --- |
| To prepare those involved in park management to | This may (should?) include rangers or other staff, concessionaires and volunteers |
| (i) make informed and environmentally sensitive decisions about the development and management of recreational opportunities in the park, | We do not see it as appropriate to focus here upon any other aspects of recreation, e.g., leadership, health and safety, etc. |
| (ii) identify and monitor the impacts of recreation upon the environment, and | Again, this demands the capacity to recognise what is important and so to make informed judgements about monitoring |
| (iii) determine and implement actions to eliminate or limit these impacts. | No point in monitoring if no action can be taken upon identified problems. |

- TARGET  AUDIENCE

As noted above, we see the need to potentially include three different groups of personnel. Parks staff are clearly a priority, and were assumed in the original brief. However, we believe that effective partnership with concessionaires will be greatly enhanced if they are involved in the same program and helped to develop understandings in common with Parks staff. More importantly, there are already examples where concessionaires assist staff in maintenance and in the informal monitoring as is already carried out.

Their involvement in management and monitoring would often increase cost-effectiveness, even just in reducing duplication of travel, and at the same time, would enhance the quality of their own operation.

Similarly, many park visitors would see themselves as stakeholders and would willingly assist as volunteers in undertaking monitoring and corrective action. We are well aware of other examples where their entry into more remote areas has provided a  useful extension of monitoring activity which could not have been carried out by staff.

We also recommend that all these three groups should share in a common training program, rather than establishing separate programs for each. The interaction between groups would, in itself, enhance the overall quality of learning.

We again seek the opinions of the Steering Committee.

2.  Locations and Venue for Training

In each area where training was to be conducted, we would recommend that a suitable field site within the area should be identified within relatively easy reach of an appropriate indoor venue. We assume a two-day program (offered both on mid-week and week-end dates) and in some areas this will mean finding low-cost accommodation.

The field site should :

- include at least 3 ROS classes

- demonstrate a range of management issues and potential problems

- a reasonable level of availability of resource and visitor data

As we noted in our earlier paper, places such as McKillop’s Bridge and Native Dog Flat would be a useful central core for such a site.

- CURRICULUM	-  An  Indicative  Summary

Day One

- The recreation-environment nexus

The relationship need not be a conflictual one, and in fact, properly managed

recreation may even enhance environmental values.

Managing opportunity, not program.

- An overall scheme for recreation planning

Integrating recreation development with environmental quality control

The place of information - what information ?

- The Recreation Opportunity Spectrum

The ROS principles

Criteria for defining opportunity on the ground

Implementation :  Field Exercise

Review and summary

- Knowing the recreational visitors

The VAMP approach

Identifying VAMP categories of visitors

Using those categories in planning and management

Relating VAMP categories to ROS classes :  Desk Exercise

Review and Summary

Day Two

- Managing for Environmental quality

The various tools - LAC, VIM, etc.

A unified approach

Eight steps

- First Steps

Getting the context right

Reviewing the current situation

Establishing the quality team

Who else should be involved, and in what way ?

Defining issues and concerns

G. Some Specific Objectives

Setting recreational objectives in terms of desired experiential outcomes

Defining desired environmental conditions

Desk Exercise

H. Defining Environmental Management Units

The basis of defining management units

Similar environmental character

Identifying recreational activities

Potential common threats and impacts

Setting boundaries :  Field Exercise

I. Selecting quality indicators and setting standards

Field Exercise continued

Characteristics of good indicators

Selecting useful indicators

- Monitoring methods

An overview of potential methods

Desk Exercise

- Planning for Change

Identifying acceptable strategies

Affordable, practical, effective.

Course review and evaluation.

- 4.  COURSE  MATERIALS

Available documentation on the study area for reference, including

our report Vol. 2.

For each six (or other working group number) attendees

Topographic map

Other maps, including at least a simple geological plan and vegetation map

For each person

Main Report (our vol. 1) as textbook

Training Workbook (our Vol. 3)

Photocopies of the relevant section of the topo map